## Sheet1
Vendor Risk Register
Organization: NovaBridge Pvt. Ltd. ¦ Version: 1.0 ¦ Date: April 2026 ¦ Owner: GRC Team
Risk ID | Vendor Name | Risk description | Inherent Risk | Controls Effectiveness | Residual Risk | Treatment | Risk Owner | Review Date
R01 | CloudNest Inc. | Cloud infrastructure outage causes full NovaBridge service disruption | Critical | Strong | Medium | Mitigate : enforce SLA with RTO/RPO, multi-region failover requirement | IT Team | 2026-07-01
R02 | CloudNest Inc. | Sensitive data breached due to cloud misconfiguration | Critical | Strong | Medium | Mitigate : quarterly cloud security config review, enforce encryption standards | IT Team | 2026-07-01
R03 | KYC-Pro Solutions | Fourth-party risk gap, No formal security assessment conducted for TextScan | High | Moderate | Medium | Mitigate : Formal Risk assessment before vendor risk onboarding | Security team | 2026-07-01
R04 | KYC-Pro Solutions | Unauthorized access to sensitive(PII) shared due to weak MFA | High | Moderate | Medium | Mitigate : MFA must be implemented for all employees and users | Security team | 2026-07-01
R05 | KYC-Pro Solutions | Risks due to unpateched and 0-day vulnerabilities present in their application | High | Moderate | Medium | Mitigate: Perform Frequent VAPT assessment to identify unpatched and 0-day vulnerabilities and patch them | Security team | 2026-07-01
R06 | SwiftMail Corp. | Account takeover due to weak authentication to vendor dashboard | High | Moderate | Medium | Mitigate : Implement proper IAM and MFA on Vendor dashboard | Security team | 2026-07-01
R07 | SwiftMail Corp. | Outages causing failed OTPs, invoices, alerts, or reminders | High | Moderate | Medium | Mitigate : Should have proper backup services to manage until recovery is done | IT Team | 2026-07-01
R08 | TalentBridge | Employee PII and salary data leaked due to weak security controls at TalentBridge | Medium | Moderate | Medium | Mitigate — contractually require TalentBridge to implement encryption, access controls, and report breaches within 72 hour | HR Head | 2026-07-01
R09 | TalentBridge | Payroll processing failure or delay causing non-payment of employees and labour law violations | Medium | Moderate | Medium | Mitigate — enforce SLA with processing timelines, maintain contingency payroll process internally | HR Head | 2026-07-01
R10 | PrintPack | Physical interception or theft of printed cards/letters exposing customer card details | Low | Moderate | Low | Mitigate — require secure courier, tamper-evident packaging, and delivery confirmation | Operations Head | 2026-07-01
R11 | PrintPack | Improper disposal of rejected or misprinted cards exposing partial card data | Low | Moderate | Low | Mitigate — contractually require certified destruction of all misprints with destruction certificate provided to NovaBridge | Operations Head | 2026-07-01